## Gantt Chart
Flick Time Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | [Flick Time] |  |  |  |  | COMPANY NAME | [6 empty] | [SAPIENZA]
PROJECT DEVELOPERS |  | [Davood Sh , Giuseppe D] |  |  |  |  | DATE | [6 empty] | 2024-01-12
WBS NUMBER | TASK TITLE | ESTIMATED DAYS | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | 2 | 2024-01-12 | 2024-01-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | 1 | 2024-01-15 | 2024-01-16 | 1 | 100% | bar: WEEK 2 W
1.2 | Research | 5 | 2024-01-15 | 2024-01-21 | 6 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Projections | 5 | 2024-01-16 | 2024-01-22 | 6 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Stakeholders | 4 | 2024-01-18 | 2024-01-22 | 4 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Guidelines | 3 | 2024-01-19 | 2024-01-22 | 3 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Project Initiation | 1 | 2024-01-23 | 2024-01-23 | 0 | 100% | bar: WEEK 3 F
2 | Project Setup and Configuration
2.1 | Set up development environment (IDE, Git repository). | 3 | 2024-01-24 | 2024-01-27 | 3 | 100% | bar: WEEK 4 W to WEEK 4 F
2.2 | Create initial project structure. | 4 | 2024-01-26 | 2024-01-29 | 3 | 100% | bar: WEEK 4 R to WEEK 5 T
2.3 | Define project scope and objectives. | 1 | 2024-01-29 | 2024-02-01 | 2 | 100% | bar: WEEK 5 M to WEEK 5 W
2.4 | Gather functional and non-functional requirements. | 2 | 2024-02-01 | 2024-02-03 | 2 | 100% | bar: WEEK 5 W to WEEK 5 F
2.5 | Define user stories and prioritize features. | 3 | 2024-02-05 | 2024-02-07 | 2 | 100% | bar: WEEK 6 M to WEEK 6 T
2.6 | Create backlog and roadmap. | 2 | 2024-02-07 | 2024-02-09 | 2 | 100% | bar: WEEK 6 M to WEEK 6 T
2.7 | Design system architecture (model-view-controller). | 4 | 2024-02-07 | 2024-02-11 | 4 | 100% | bar: WEEK 6 M to WEEK 6 R
2.8 | Select technology stack (Spring Boot, Thymeleaf, Spring Security, PostgreSQL). | 2 | 2024-02-10 | 2024-02-12 | 2 | 100% | bar: WEEK 6 R to WEEK 6 F
2.9 | Define API contracts and data models | 2 | 2024-02-11 | 2024-02-12 | 1 | 100% | bar: WEEK 6 F
3 | Backend Development
3.1 | Set up Spring Boot project with necessary dependencies. | 1 | 2024-02-12 | 2024-02-13 | 1 | 100% | bar: WEEK 7 M
3.2 | Configure database connection and ORM (Spring Data JPA). | 2 | 2024-02-13 | 2024-02-15 | 2 | 100% | bar: WEEK 7 M to WEEK 7 T
3.3 | Implement basic CRUD operations for entities. | 2 | 2024-02-15 | 2024-02-18 | 3 | 100% | bar: WEEK 7 T to WEEK 7 F
3.4 | Implement user authentication and authorization using Spring Security. | 2 | 2024-02-19 | 2024-02-21 | 3 | 100% | bar: WEEK 8 M to WEEK 8 W
3.5 | Create user registration, login, and logout functionalities. | 3 | 2024-02-20 | 2024-02-22 | 3 | 100% | bar: WEEK 8 T to WEEK 8 R
3.6 | Develop services layer to handle business logic. | 2 | 2024-02-22 | 2024-02-24 | 2 | 100% | bar: WEEK 8 R to WEEK 8 F
3.7 | Implement repository layer for database interactions. | 4 | 2024-02-26 | 2024-03-01 | 5 | 100% | bar: WEEK 9 M to WEEK 9 F
3.8 | Set up data validation and error handling. | 3 | 2024-02-27 | 2024-03-01 | 4 | 100% | bar: WEEK 9 T to WEEK 9 F
4 | Frontend Development
4.1 | Set up frontend project structure (HTML, CSS). | 2 | 2024-03-04 | 2024-03-05 | 1 | 100% | bar: WEEK 10 M
4.2 | Design user interface wireframes and layouts. | 4 | 2024-03-05 | 2024-03-08 | 4 | 100% | bar: WEEK 10 T to WEEK 10 F
4.3 | Create static pages and navigation. | 4 | 2024-03-11 | 2024-03-15 | 5 | 100%
4.4 | Develop UI components for displaying movie and artist information. | 4 | 2024-03-18 | 2024-03-22 | 5 | 100% | bar: WEEK 12 M to WEEK 12 F
4.5 | Implement basic navigation and routing using Thymeleaf. | 4 | 2024-03-19 | 2024-03-22 | 4 | 100% | bar: WEEK 12 T to WEEK 12 F
4.6 | Integrate with backend APIs for fetching and updating data. | 4 | 2024-03-19 | 2024-03-22 | 4 | 100% | bar: WEEK 12 T to WEEK 12 F
5 | Project Performance / Monitoring
5.1 | Execute unit tests for backend services and repositories. | 4 | 2024-03-25 | 2024-03-28 | 4 | 100% | bar: WEEK 13 M to WEEK 13 R
5.2 | Ensure code coverage and quality. | 4 | 2024-04-01 | 2024-04-05 | 5 | 100%
5.3 | Perform integration testing for backend APIs and frontend components. | 3 | 2024-04-02 | 2024-04-05 | 3 | 100% | bar: WEEK 14 T to WEEK 14 F
5.4 | Address and fix any reported bugs or issues. | 3 | 2024-04-08 | 2024-04-11 | 3 | 100% | bar: WEEK 15 M to WEEK 15 W
5.5 | Deploy application to staging environment for final testing. | 1 | 2024-04-11 | 2024-04-12 | 1 | 100% | bar: WEEK 15 W to WEEK 15 R
5.6 | Monitor application performance | 2 | 2024-04-15 | 2024-04-17 | 2 | 100% | bar: WEEK 15 R to WEEK 15 F
5.7 | Address any post-launch issues or enhancements. | 2 | 2024-04-16 | 2024-04-18 | 2 | 100% | bar: WEEK 15 R to WEEK 15 F